## Environment_preparation
SR No | Task Details | Command | Comment | WBC
1 | Verify the environment is up and running
2 | Copy DDL and scripts
3 | Remove old log files/Tmp files if any
4 | Remove the exisitng tables if any
5 | Create directory for TDDD and DBQL data
6 | Data copy

## Run_Book
Task | Step_Name | Batch file/Script File | Manual/Automated | UseCase | Comment
Copy Scripts at local drive | step1 |  | Manual
Create STG and Core DDLs - AWS | step2 | DDL_STG_CORE_AWS.bteq | Manual
Execute TPT Script(STG) - AWS | step3 | STG_ORDRES.tpt | Manual
Execute Bteq Script(NOS STG) - AWS | step4 | NOS_ORDERS_STG.bteq | Manual
Execute Bteq Script(CORE) - AWS | step5 | ORDERS_L0AD.bteq NOS_ORDERS_LOAD.bteq | Manual
Execute Semantic DDLs - AWS | step6 | SEM_DDL_ORDERS_AWS.bteq | Manual
Execute Bteq Script(Data Load Access) - AWS | step7 | SEM_ORDERS.bteq SEM_NOS_ORDERS.bteq | Manual
Execute Bteq Script(Read Data Access) - AWS | step8 | SEM_ACCESS_VIEWS.bteq | Manual
Create STG and Core DDLs - Azure | step9 | DDL_STG_CORE_AZURE.bteq | Manual
Execute TPT Script(STG) - Azure | step10 | TPT_STG_AZURE_RETAIL_CUSTOMER.tpt TPT_STG_AZURE_RETAIL_PRODUCT.tpt TPT_STG_AZURE_RETAIL_STORE.tpt TPT_STG_AZURE_TRANSACTION.tpt | Manual
Execute Python Script(STG) - Azure | step11 | ONELINE_PRODUCTS_LOAD.py | Manual
Execute Bteq Script(CORE) - Azure | step12 | CORE_AZURE_RETAIL_CUSTOMER_L0AD.bteq CORE_AZURE_ONLINE_PRODUCT_L0AD.bteq CORE_AZURE_RETAIL_AND_ONLINE_PRODUCT_L0AD.bteq CORE_AZURE_RETAIL_PRODUCT_L0AD.bteq CORE_AZURE_RETAIL_STORE_L0AD.bteq CORE_AZURE_TRANSACTION_LOAD.bteq | Manual
Execute Temporal Table Scrpt - Azure | step13 | TEMPORAL_CUSTOMER.sql | Manual
Execute Semantic DDLs - Azure | step14 | SEM_AZURE_ONLINE_PRODUCT_TABLE.bteq SEM_AZURE_RETAIL_TRANSACTION_TABLE.bteq SEM_AZURE_ONLINE_PRODUCT_ORDER_VW.bteq SEM_AZURE_RETAIL_STORE_VW.bteq SEM_AZURE_RETAIL_TRANSACTION_VW.bteq | Manual
Execute Bteq Script(Semantic) - Azure | step15 | SEM_ONLINE_PRODUCTS_ORDERS_INSERT.bteq | Manual
Execute Queue and Procedure - Azure | step16 | RETAIL_CUSTOMER_QUEUE.sql | Manual
Execute Semantic Macro - Azure | step17 | MACRO__GET_STORE_DATA.sql MACRO_CLOSEST_STORE.sql | Manual
Execute Semantic Extract - Azure(Python) | step18 | EXPORT_CUSTOMER.py | Manual
Execute TPT Script - Azure(CSV) | step19 | CUSTOMER_DELTA_EXPORT.tpt PRODUCT_ORDER_EXPORT.tpt PRODUCT_EXPORT.tpt RETAIL_STORE_EXPORT.tpt | Manual

## Validate_Tables
Note : - make sure to replace database with respective quicklook id
step_name | Batch File | Step_Table_Name | Comments | Compare Qlik QVD
Once deployment gets completed we need to verify the DDLs
Count of records |  | sel count (*) from STG_AWS_ORDERS ; sel count (*) from STG_NOS_AWS_ORDERS ; sel count (*) from STG_AZURE_RETAIL_CUSTOMER ; sel count (*) from STG_AZURE_RETAIL_ONLINE_ PRODUCT ; sel count (*) from STG_AZURE_ONLINE_PRODUCT ; sel count (*) from STG_AZURE_RETAIL_STORE ; sel count (*) from STG_AZURE_RETAIL_TRANSACTION ; sel count(*) from CORE_AWS_ORDERS_VW ; sel count(*) from CORE_NOS_AWS_ORDERS_VW ; sel count(*) from CORE_AZURE_RETAIL_CUSTOMER_VW ; sel count(*) from CORE_AZURE_RETAIL_PRODUCT_VW ; sel count(*) from CORE_AZURE_ONLINE_PRODUCT_VW ; sel count(*) from CORE_AZURE_RETAIL_STORE_VW ; sel count(*) from ORE_AZURE_RETAIL_TRANSACTION_VW ; Sel count(*) from SEM_NOS_AWS_ORDERS; Sel count(*) from SEM_AWS_ORDERS; Sel count(*) from SEM_ORDER_QTY_BY_CUSTOMER_ID_VW; Sel count(*) from SEM_ORDER_QTY_BY_STORE_ID_VW; Sel count(*) from .SEM_ORDER_QTY_BY_CUSTOMER_STORE_ID_VW; | Query can be created on the fly as well
Export file validation